## ProjectSchedule
TCR Violations Analysis | [6 empty] | ► Watch How to Make a Gantt Chart in Excel
Umass Amherst Water Research Team |  | Project Start: | 2026-02-27
Ava Johnson |  | End: | 2026-04-14
|  | Display Week: | 1 |  |  | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13
 | time axis 2026-02-23 to 2026-04-19
| Week | PROGRESS | START | END | DAYS | time axis 2026-02-23 to 2026-04-19
Phase 1 Technical
Review client request, rubrud, and deliverables | 1 | 100% | 2026-02-27 | 2026-03-05 | 7
Select 5 states across 5 EPA regions | 1 | 100% | 2026-03-07 | 2026-03-09 | 3
Define criteria for small vs. large systems | 1 | 100% | 2026-03-07 | 2026-03-09 | 3
Phase 2 Data acquisition and cleaning
Explore SDWIS interface and identify required reports | 2 to 3 | 100% | 2026-03-09 | 2026-03-22 | 14
Download TCR violation report for all 5 states | 2 to 3 | 100% | 2026-03-09 | 2026-03-22 | 14
Organize raw data files and document file structure | 2 to 3 | 100% | 2026-03-09 | 2026-03-22 | [57 empty] | Task Dependencies: The tasks in this project follow a logical sequence in which each phase builds on the work completed in the previous one. The project begins with reviewing the client request, which enables the selection of three states and the definition of system‑size criteria. Once these foundational decisions are made, the team can explore SDWIS interfaces, identify the required reports, and download the TCR violation data for all selected states. After downloading, the raw files must be organized before writing the initial Python cleaning script, which then allows the dataset to be standardized, classified by system size, and fully QA/QC‑checked. With a clean dataset prepared, the analysis phase can begin by generating summary tables, creating figures of violations over time, and comparing small versus large systems, followed by sensitivity checks to refine results. Once the analysis is complete, the full report can be drafted, then formatted and finalized. In parallel with the analytical work, the GitHub repository and README can be created, but uploading cleaned data, final scripts, figures, and the completed report depends on finishing the analysis and writing phases. Ultimately, all deliverables—including summary tables, figures, cleaned data, and the final report—are uploaded only after the analysis and report writing are fully completed.
Write intial python cleaning script and standardize variable names, units, and date formats | 2 to 3 | 100% | 2026-03-09 | 2026-03-22
Classify systems as small vs. large and QA/QC cleaned dataset | 2 to 3 | 100% | 2026-03-09 | 2026-03-22
Phase 3 Analysis and Visualization
Create summary tables of TCR violations by state over time | 4 to 5 | 100% | 2026-03-26 | 2026-04-05 | 11
Generate figures of violations vs. year for each state | 4 to 5 | 100% | 2026-03-26 | 2026-04-05
Analyse differences between small and large systems | 4 to 5 | 100% | 2026-03-26 | 2026-04-05
Sensitivity checks and refinement | 4 to 5 | 100% | 2026-03-26 | 2026-04-05
Phase 4 Report Writing
Write full report | 5 to 7 | 100% | 2026-03-26 | 2026-04-08 | 14
Format and finalize report | 7 | 100% | 2026-04-11 | 2026-04-13 | 3
Phase 5 Deliverables and Submittal
Create GitHub repository and folder strucutre | 7 to 8 | 100% | 2026-03-15 | 2026-03-18 | 4
Create README describing porject, data, and scrpits | 7 to 8 | 100% | 2026-03-18 | 2026-03-21
Finalize analysis scripts and annotate code | 7 to 8 | 100% | 2026-04-03 | 2026-04-08
Save final summary tables and figures | 7 to 8 | 100% | 2026-04-06 | 2026-04-09
Upload code and cleaned data to GitHub | 7 to 8 | 100% | 2026-04-13 | 2026-04-14
Upload summary tables and figures | 7 to 8 | 100% | 2026-04-14 | 2026-04-14
Upload final report to GitHub and submit | 7 to 8 | 100% | 2026-04-14 | 2026-04-14
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.